|  |  |  |
| --- | --- | --- |
| **Production Schedule** | **Name: Eloise**  | **Project Title: Fmp**  |
| **Date/Time** | **What’s To Be Done & Where** | **Who Is responsible** | **Resources** | **Changes Made** | **Date Completed** |
| **5/03/25** | **Brockat hall to location recce**  | **Eloise****Lily** **Aimee**  | **Our phones** **Location recce sheet**  | **We did not end up being able to film here because we would have had to pay £10,000 for the golf course to close for us to be able to film.**  | **5/03/25** |
|  **5/03/25**  | **Tewin water estate location recce**  | **Eloise****Lily** **Aimee** | **Our phones** **Location recce sheet** | **Decided to film here as it fit the fairy core.** | **5/03/25**  |
| **27/03/25** | **Sues garden location recce**  | **Eloise****Lily** **Aimee**  | **Our phone's location recce sheet**  | **Decided to film here as brocket hall was a failure and sues garden is beautiful.** | **27/03/25** |
| **31/03/25**  | **Tewin water estate filming**  | **Eloise****Lily** **Aimee** | **Props** **Camera** **Tripod** **Speaker**  | **No script we just decided to film us dancing and enjoying our time together**  | **31/03/25**  |
| **2/04/25** | **Sues garden filming**  | **Eloise** **Lily** **Aimee**  | **Props** **Camera** **Tripod** **Speaker**  | **No changes made**  | **2/04/25**  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| **Date/Time** | **What’s To Be Done & Where** | **Who Is responsible** | **Resources** | **Changes Made** | **Date Completed** |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |